## Sheet1
CAPA ID | Nonconformity | Root Cause | Corrective Action | Preventive Action | Owner | Target Date | Verification Method | Status
CAPA-001 | NC-001 | No effective tracking and escalation mechanism existed to ensure completion of scheduled access reviews | Complete the missed Q2 access review and review outstanding access exceptions | Implement automated review reminders, assigned review ownership, escalation procedures, and management monitoring | IT Director | 2026-08-31 | Verify Q3 and Q4 access reviews are completed on time with documented evidence | Open
CAPA-002 | NC-002 | Vendor management process focused on onboarding and lacked an operational periodic reassessment program | Perform overdue reassessments for high-risk and critical vendors | Implement a risk-based vendor reassessment schedule with automated due-date tracking and escalation | Head of Vendor Risk | 2026-09-30 | Verify all high-risk and critical vendors have current reassessments according to the approved schedule | Open
CAPA-003 | NC-003 | Monitoring responsibilities and documentation requirements were not clearly operationalized | Establish documented ongoing monitoring activities for active vendors | Define monitoring ownership, minimum monitoring activities, frequency, and evidence retention requirements | Head of Vendor Risk | 2026-09-30 | Review monitoring evidence for selected vendors over two consecutive review periods | Open
CAPA-004 | NC-004 | Remediation tracking and evidence retention practices were not consistently standardized | Complete missing closure documentation for identified access review exceptions | Standardize remediation ticket requirements and closure evidence expectations | IAM Manager | 2026-08-31 | Select subsequent access review exceptions and verify complete closure evidence is retained | Open