## Sheet1
Risk Treatment Plan : SecureFusion Technologies
Document ID: SF-ISMS-RTP-001 | RTP_001
Version: 1.0
Document Owner: Chief Information Security Officer (CISO)
Assessment Reference: SF-ISMS-RR-001 | ASP001
Date: 2026-07-21
Classification: Internal Use
Risk ID | Description | Inherent Rating | Treatment | Selected Control(s) | Specific Action | Owner | Budget | Target Date | Residual Rating | Success Criteria | Status
R1 | Privileged AWS, Azure, or Microsoft 365 accounts may be compromised, allowing unauthorized access to sensitive systems, modification of configurations, or disruption of critical services. | 20 — Critical | Reduce | 5.15 Access Control; 5.18 Access Rights; 8.2 Privileged Access Rights | Implement centralized privileged access management, enforce phishing-resistant MFA for privileged accounts, conduct quarterly privileged access reviews, remove standing access where feasible, and implement time-limited administrative access for critical environments. | IAM Manager | Medium | 2026-10-31 | 8 — Medium | 100% of privileged accounts inventoried; 100% protected by MFA; quarterly access reviews completed; unauthorized standing privileged access reduced; no unresolved critical access exceptions. | Not Started
R2 | Customer PII may be accessed, disclosed, or misused by unauthorized individuals due to excessive access, compromised accounts, or incorrect security configurations. | 20 — Critical | Reduce | 5.15 Access Control; 5.23 Cloud Services Security; 5.34 Privacy and Protection of PII; 8.24 Use of Cryptography | Complete PII data discovery and classification, review access to PII repositories, enforce least privilege, validate encryption at rest and in transit, and perform periodic privacy and cloud configuration reviews. | Privacy Officer | Medium | 2026-11-30 | 8 — Medium | All critical PII repositories identified and classified; access reviews completed; encryption requirements validated; no critical unauthorized access findings remain open. | Not Started
R3 | Malware or ransomware may compromise remote employee endpoints and connected systems, resulting in data loss, operational disruption, or unauthorized access. | 16 — Critical | Reduce | 6.3 Information Security Awareness, Education and Training; 8.7 Protection Against Malware; 8.13 Information Backup | Achieve full EDR coverage for managed endpoints, improve endpoint security baselines, conduct recurring phishing simulations and role-based awareness training, and validate isolated backup recovery through restoration testing. | Security Operations Manager | Medium | 2026-09-30 | 6 — Medium | 100% of managed endpoints covered by EDR; critical endpoint security gaps remediated; training completion exceeds 95%; successful restoration tests completed. | Not Started
R4 | Misconfiguration or failure of AWS or Azure services may expose sensitive information or interrupt critical business operations. | 15 — Critical | Reduce | 5.23 Information Security for Use of Cloud Services; 5.30 ICT Readiness for Business Continuity; 8.22 Segregation of Networks | Establish documented AWS and Azure security baselines, implement continuous configuration monitoring, review shared-responsibility requirements, strengthen network segmentation, and define recovery requirements for critical cloud services. | Cloud Security Lead | High | 2026-12-31 | 8 — Medium | Critical cloud services assessed against approved baselines; high-risk misconfigurations remediated within defined SLA; segmentation validated; recovery requirements documented. | Not Started
R5 | Employees or contractors may be deceived into disclosing credentials, sensitive information, or performing unauthorized actions through phishing or social engineering. | 20 — Critical | Reduce | 5.7 Threat Intelligence; 6.3 Information Security Awareness, Education and Training; 8.7 Protection Against Malware | Implement a recurring security awareness program, conduct realistic phishing simulations, provide targeted training for high-risk roles, strengthen email threat detection, and establish a formal process for reporting suspected phishing. | Security Awareness Manager | Medium | 2026-09-30 | 8 — Medium | Training completion exceeds 95%; phishing reporting rate improves; repeat failure rates decrease; high-risk users receive targeted training; suspicious email reporting process is operational. | Not Started
Treatment Decision Summary
Treatment | Number of Risks
Reduce | 5
Transfer | 0
Avoid | 0
Accept | 0
All five selected risks will initially be reduced through additional security controls and improvements.
Risk Treatment Prioritization
Priority | Risk ID | Current Rating | Target Residual Rating | Primary Treatment Focus
1 | R1 | 20 — Critical | 8 — Medium | Privileged access management
2 | R5 | 20 — Critical | 8 — Medium | Phishing resilience and awareness
3 | R2 | 20 — Critical | 8 — Medium | PII access governance and protection
4 | R3 | 16 — Critical | 6 — Medium | Endpoint and ransomware protection
5 | R4 | 15 — Critical | 8 — Medium | Cloud security and resilience
Treatment Plan Governance
Risk treatment actions will be tracked by the assigned risk owner and reviewed by the CISO or designated ISMS governance body.
Treatment status will be updated as follows:
Not Started — Action has been approved but work has not begun.
In Progress — Treatment activities are actively being performed.
Blocked — Progress is prevented by a documented dependency or issue.
Complete — Defined treatment actions have been implemented and validated.
Accepted — Residual risk has been formally accepted by authorized management.
Residual risk ratings will be reassessed after treatment actions are implemented and their effectiveness has been validated.