## Sheet1
NC ID | Finding ID | Nonconformity | Severity | Root Cause | CAPA ID | Status | Verification Date
NC-001 | F-001 | Q2 quarterly access review was not performed or documented | Major | No effective tracking and escalation mechanism existed to ensure completion of scheduled access reviews | CAPA-001 | Open
NC-002 | F-002 | Periodic vendor reassessments were not performed after initial onboarding | Major | Vendor management process focused on onboarding and lacked an operational periodic reassessment program | CAPA-002 | Open
NC-003 | F-003 | Ongoing vendor security monitoring was not consistently documented | Minor | Monitoring responsibilities and documentation requirements were not clearly operationalized | CAPA-003 | Open
NC-004 | F-004 | Closure evidence for selected access review exceptions was incomplete | Observation / Improvement Opportunity | Remediation tracking and evidence retention practices were not consistently standardized | CAPA-004 | Open